## Week-by-Week Plan
| MarComm |  |  |  |  | Development |  | Mailed Collateral |  | Video Production
Week of: | Program | Design Collateral | Social | Emails | Featured Guest/Media | Tickets and Sponsorships | Event Page | Mailed Boxes | Awards | Event Filming/Production | OHU Video Production
Owner | Allie/Miriam | Miriam | Allie | Allie | Scotty | Vanessa/Tonya | Tonya/Vanessa/Jake | ESP/Mandy | Gail | ESP/Jake | Jake
2021-02-01 | [5 empty] | Research One Cause and Greater Giving Capabilities |  | Research Cookie and Coffee Vendors
2021-02-08 |  |  |  |  | Outreach to potencial guest | Finalize ticket levels and sponsorships (Todd) |  | Identify vendors and price points |  |  | Planning Meeting
2021-02-15 |  | Toolkit and Design element package planning meeting (MarComm) |  |  |  | Final Ticketing and Event platform decision needed - One Cause contract purchase |  | Identify tote vendor and price point | Awardees finalized (Todd)
2021-02-22 | [5 empty] | Ticket page live by EOW |  | Present proofs at weekly check-in | Award recipients informed of their award (Todd) |  | Evergreen Video: Concept pitches to Scotty/Todd
[6 empty] | Add to OHU events on website (Jake) |  |  | Begin coordinating with Gail
2021-03-01 |  |  | 3/1: save the date social post | 3/1: Save the date email | Guest identified? |  | Tonya/Vanessa/ESP begin evaluating night of donation transactions | Final decision on vendors/amounts | 3/4: Meet with Gail and Mandy |  | Mission Moments: Concepts for all three videos complete
Evergreen Video: Identify all characters
2021-03-08 | 3/8: Begin program design (Miriam) | Comms team draft of toolkit complete by EOW | 3/10: reminder to purchase tickets/be a sponsor social post |  | Masks for press conference ordered |  |  |  | 3/8: Names for awards finalized and sent to Gail | ROS confirmed with ESP | Mission Moments: Identify all characters
3/12: Proofs received from vendor
2021-03-15 |  | 3/15: Send toolkit for final review |  | 3/18: Follow-up email about ticket sales (with current list of sponsors) |  |  |  |  | 3/15: Proofs reviewed by Todd | Schedule pre-recordings (Awardees, presenters) | Evergreen Video: Filming begins
3/17: Feedback on toolkit due
3/19: Final toolkit complete EOD
2021-03-22 | 3/26: Copy for program due | 3/22: Toolkit due to ambassador boards |  |  |  |  | Program design needs event URL |  | 3/22: Awards shipped to recipients | Scripts for Awardees and Presenters Due | Mission Moments: Begin Filming
|  | Sent out to Ambassador boards (Mandy) | [8 empty] | Evergreen Video: Filming Complete
2021-03-29 | Program printing/delivery quote |  |  |  | Masks for press conference delivered |  | Tonya/Vanessa/ESP final night of donation transaction plan complete |  |  |  | Mission Moments: Complete Filming
| 3/29: Pictures and bios due to Miriam |  | 3/31: keynote announcement social post | 3/31: Keynote Speaker announcement email sent | [6 empty] | Evergreen Video: Editing begins
2021-04-05 | MarComm review of program design |  | 4/5: sponsorships and ticket sales social post |  | 4/8: Press Conference in FL |  |  |  |  | Any materials for keynote and celeb Q&A due | Mission Moments: Editing begins
|  |  | 4/7: social post teasing forward to press conference, presenting Flaviane with the President's Award | [7 empty] | Evergreen Video: Rough Cut to Scotty and Allie
2021-04-12 | Team review of program design |  | 4/8: live stream press conference presenting Flaviane with President's Award on social | [7 empty] | Mission Moments: Rough Cuts due to Scotty and Allie
|  |  | 4/12: social post announcing award winners | [7 empty] | Evergreen Video: Fine Cut to Scotty and Todd
2021-04-19 | Final program design (without sponsors) complete |  | Sponsorship post | 4/19: Updated ticket list needed for updated email list |  |  | Begin creating event page with ESP (Jake) |  |  |  | Mission Moments: Fine cuts due to Scotty and Todd
Evergreen Video: Final Approval
[6 empty] | Updated ticket list needed for updated email list |  |  |  |  | Mission Moments: Final approval
2021-04-26 | List of sponsors due |  | 4/26: last call for sponsors social post | 4/26: Last call for sponsorship email sent (deadline to be included in program as sponsor is 4/30) |  | 4/30: Remove sponsorships from page | Tonya/Vanessa/ESP test event page for method of adjusting the totals night-of |  |  | 4/28: All pre-recordings complete | 4/28: All videos due to ESP
4/30: Last day for printed recognition from any tickets/sponsorships
2021-05-03 | 5/3: Final program design with sponsors updated |  | Last call for boxes tickets post | Updated ticket list needed for updated email list |  | Updated ticket list needed for updated email list | 5/6: Event page live internally (Jake) | 5/3: Coffee ships from roaster |  |  | 5/4: Evergreen video used in May 4 event
2021-05-10 | Programs delivered to office |  | Last chance to purchase tickets w/ boxes social post | 5/10: last chance for coffee and cookies box email (deadline to purchase is 5/12) | Event press release? | 5/12: box ticket cut off | 5/13: Event page live to public (Jake) | 5/10: Materials for boxes (minus cookies) in the packing location TBA |  | 5/11: First cut client review
5/13: Team feedback on irst cut due
Kate/Todd/ESP live appeal walk-through?
2021-05-17 |  |  | Last reminder post | 5/17: Last chance to purchase viewing tickets email (deadline to purchase is viewing tickets is 5/19) |  | 5/19: All ticket sales cut off |  | 5/17: Boxes shipped |  | 5/17: Final cut review
|  |  | Day of event post ("live" tweet during event, pre-scheduled posts about award winners, etc.) | 5/19 Email ticketholders link |  | Updated ticket list needed for updated email list (ticketholder email) |  |  |  | 5/18: Final cut review feedback due
|  |  | 5/21: thank you to attendees and sponsors social posts | 5/20: Day of event reminder, 5/21: thank you email (1 version for donors, 1 version for attendees) |  | Updated ticket list needed for updated email list (last reminder email) |  |  |  | 5/19: Final program delivery
May 20 - An Evening of Hope Event
2021-05-24 |  |  | Video clip posts
2021-05-31
Questions:
Decisions to make:

## Roles and Responsibilities
|  | Owner | Helper | Approver
Virtual Event | Mailed Boxes | Mandy/Clarice | Gail | Todd
| Awards (allocation) | Charles/Todd
| Awards (creation/mailing) | Gail | Mandy | Todd
| Evergreen OHU Video | Jake | Miriam | Scotty/Todd
| Script for ROS | Scotty | Allie | Todd
| Streamed Live Event Program | ESP
| Awardee Scripts | Scotty
| Mission Moments | Jake
| Talking Heads in ROS | ESP | Jake | Todd
| Celebrity appearance | Todd/Scotty/ESP
Development | Sponsorship Sheet | Todd/Mandy
| Donation Management | Tonya/Vanessa
| Sponsorships | Todd/Mandy | Exec Staff
| Ticket/Sponsorship Webpage (OC or GG) | Tonya/Vanessa | Jake | Todd
Marketing/Communications | Toolkit | Jake/Allie | Miriam | Scotty/Todd
| Social Campaign | Allie | Miriam | Scotty
| Content for Ticket Webpage | Allie | Tonya/Vanessa/Miriam
| Content for Event Webpage | Allie | Tonya/Vanessa/Miriam
| Design Element Package | Miriam | Scotty
| Media Outreach | Scotty
| Program | Allie/Miriam | Miriam/Allie
| Email Invites | Allie | Scotty/Miriam | Todd

## Collateral
| Social Toolkit | Which toolkit? | Quantiity (if applicable) | Owner | Complete? | Program | Owner | Complete? | Graphic Package (Design collateral NOT in Toolkit) | Owner? | Complete? | Deadline
Contents | What is National Child Abuse Prevention Month? | All |  | Allie | Y | Front Cover Design | Miriam | N | Event Page Header | Miriam | Y | Week of Feb. 22
| What is National Foster Care Month? | All |  | Allie | Y | Mission Moment Descriptions | Allie | N | Email Design | Miriam | Y | Week of April 5
| How to get involved (Board of Directors) | BOD |  | Allie | - | Event Schedule | Jake | N | Internal Social Graphics | Miriam | Y | Week of April 5
| How to get involved (Amb. Board) | AB |  | Allie | - | Award Recipients Pictures | Jake | N | Facebook Header | Miriam | Y | Week of April 5
| How to get involved (Employees) | General |  | Allie | - | Award Recipients Bios | Allie | N
| How to get involved (General Supporters) | General |  | Allie | Y | Sponsors and logos | Mandy/Jake | N
| Social Graphics | All | 4 to 6 | Miriam | Y | Back Cover Design | Miriam | N
| Sample Social Posts | All | 4 to 6 | Allie | Y | Printing | Jake | N
| Upcoming Events | All |  | Allie | Y
| About OHU | All |  | Allie | Y
| Assembly of Deck | -- |  | Miriam | Y
| Instagram Gifs? | All | 4 | Miriam/Jake | N
| Snapchat filter? | All | 2 | Miriam/Jake | -
| Virtual Background | General/AB |  | Miriam/Jake | Y
Deadline | Week of March 22 |  |  |  |  | Week of April 28 |  |  | VARIES
Recipients | Board of Directors, Ambassador Board, General Public |  |  |  |  | All guests |  |  | All external audiences
Distribution | Email, Webpage, Social Media |  |  |  |  | Mailed to guests |  |  | NA

## Updated ROS
Start | End | Length | Action
18:45 | 18:59 | 14:00 | Pre-Show
18:59 | 19:00 | 1:00 | Sponsor Loop
19:00 | 19:00 | 0:03 | Transition Graphic
19:00 | 19:02 | 2:00 | Org Intro Video
19:02 | 19:07 | 5:00 | Welcome Remarks
19:07 | 19:07 | 0:03 | Transition Graphic
19:07 | 19:22 | 15:00 | Keynote
19:22 | 19:22 | 0:03 | Transition Graphic
19:22 | 19:24 | 2:00 | Appeal 1
19:24 | 19:24 | 0:03 | Transition Graphic
19:24 | 19:34 | 10:00 | Q&A Conversation
19:34 | 19:34 | 0:03 | Transition Graphic
19:34 | 19:36 | 2:00 | Leadership in Giving Award Presentation
19:36 | 19:38 | 2:00 | Leadership in Giving Recipient
19:38 | 19:38 | 0:03 | Transition Graphic
19:38 | 19:41 | 3:00 | Video: Mission Moment 1- Residential
19:41 | 19:41 | 0:03 | Transition Graphic
19:41 | 19:43 | 2:00 | Ermit L. Finch Impact Award Presentation
19:43 | 19:45 | 2:00 | Ermit L. Finch Impact Award Recipient

## ESP Video Records
Category | Segment(s) to Record | Speaker(s) | Materials Needed | Who needs to be part of the recording? | Initial Intro Email Sent? | Shoot Date(s)
Pre-Recorded Talking Heads | Welcome and Remarks (6:00), Closing Remarks (4:00) | Charles | Script | Todd, Scotty, Jake, ESP | Y
| Keynote (10:00) | Featured Guest – Dreion | Script | Scotty, Jake, ESP | Scotty
| Conversation (10:00) | Charles and Dreion | Talking Points | Todd, Scotty, Jake, ESP | Y
| Leadership in Giving Presentation (2:00) | Kate Shaffer | Script | Jake, ESP | Y
| Leadership in Giving Recipient (2:00) | RJ Young NOW DAVID | Script | Jake, ESP | Y
| Ermit L. Finch Impact Award Presentation (2:00) | Jonni Miklos | Script | Jake, ESP
| Ermit L. Finch Impact Award Recipient (2:00) | Howard and Chris Schnitzer | Script | Jake, ESP | Y
| President's Award Presentation (2:00) | Charles | Script | *OHU to provide footage from press event with remarks
| President's Award Recipient (2:00) | Flaviane Carvalho | Script | *OHU to provide footage from press event with remarks

## Budget
Event Cost:
Item | Cost Estimate | Actual Cost | Notes
ESP Contract
Program Printing
One Cause Contract
Coffee |  |  | Estimate: 8.00 x 150
Cookies (2 dozen) |  |  | Estimate: 15.32 x 150
Totes |  |  | Estimate: 5.49 x 150
Box shipping materials (packing slips) |  |  | Estimate: using last gala's costs
Box Packing Paper |  |  | Estimate: using last gala's costs
Box shipping |  |  | Estimate: 13.95 x 150
Awards |  |  | Estimate: using last gala's costs
Award Shipping |  |  | Estimate: medium box 13.95 x 3
Guest Speaker Fee
Post Card Invite Printing
Post Card Invite Mailing
Post Card Invite Postage
Intro Video VO Recording
Final box cost: $43.98/box
Totals: | 0

## Videos
Category | Owner | Intro | Run-Time | Speaker(s) | Materials Needed | Shoot Date(s)
Talking Heads (Zoom) | ESP/Jake/Scotty | Welcome and Remarks | 6:00 | Charles | Script
|  | Keynote | 10:00 | Featured Guest (TBA) | Script
|  | Conversation | 10:00 | Charles and Featured Guest (TBA) | Talking Points
|  | President's Award Presentation | 2:00 | Charles | Script
|  | Closing | 4:00 | Charles | Script
|  | Leadership in Giving Presentation | 2:00 | Kate Schaffer | Script
|  | Leadership in Giving Recipient | 2:00 | RJ Young | Script
|  | Ermit L. Finch Impact Award Presentation | 2:00 | Jonni Miklos | Script
|  | Ermit L. Finch Impact Award Recipient | 2:00 | Howard and Chris Schnitzer | Script
|  | President's Award Presentation | 2:00 | Charles | Script
|  | President's Award Recipient | 2:00 | Flaviane Carvalho | Script
Live | ESP/Todd | Appeal 1 | 2:00 | Kate Schaffer | Talking Points
|  | Appeal 2 | 2:00 | Kate Schaffer | Talking Points
|  | Appeal 3 | 2:00 | Kate Schaffer | Talking Points
Pre-Produced | Jake | Mission Moment 1 | 3:00 | TBA | Script and Broll
|  | Mission Moment 2 | 3:00 | TBA | Script and Broll
|  | Mission Moment 3 | 3:00 | TBA | Script and Broll
|  | Intro Video (Evergreen) | 3:00 | NA | NA
| ESP | Pre-show | 14:00 | NA | Fast Facts and Material for ESP
|  | Sponsor Loop | 1:00 | NA | Sponsors, names, and logos
|  | Transition Graphics | Varies | NA | Segment names and Award Names for ESP
|  | Closing Credits and Thank You's | 2:00 | NA | Sponsor names for ESP

## Mission Moments Production
Evergreen |  | Mission Moment 1 |  | Mission Moment 2 |  | Mission Moment 3
|  | Line of Service | Residential | Line of Service | FL - Successful Adoption | Line of Service | ELCD - Parent Success through COVID
"Day in the life of... Pivot"
Characters |  | Characters |  | Characters |  | Characters
Point Person |  | Point Person |  | Point Person |  | Point Person
Broll Needed |  | Broll Needed |  | Broll Needed |  | Broll Needed
Run Time | 3:00 | Run Time | 3:00 | Run Time | 3:00 | Run Time | 3:00
Brainstorm:
Conveys the mission of OHU |  |  | Voice of counselor -- day in the life of youth |  | Start with asking Sarah |  | Allie has a quote from a parent in ELCD, want to use the conenction to find a character
Our Services |  |  | Interview staff, create script that's first person, voice over broll from actual residential with no ppl in it |  |  |  | Broll, pictures, staff video in the center
All lines of service (including behavioral health) |  |  | Rebound – someone over 18 to talk to? |  |  |  | Aurora -- can get video of the center -- big facility -- walk through, walking into the center
Combo of 125 video and Gucci Video
Getting "Hope" art submissions for an intro sequence?
Poem?
Historical Figures -- most impactful OHU members over the years?
Drop pins on the map for locations?

## Tickets and Sponsorships
| Presenting Sponsor | Keynote sponsor | "Patron" Sponsor | "Host" sponsor | "Champion" sponsor | Viewing Ticket
| 25000 | 10000 | 5000 | 1500 | 150 | 75
Recorded welcome message for the event | X
Media interview promotion | X | X
Inclusion in Media Coverage | X | X
Recognition during the event | X | X | X
Invitation and advance print materials recognition* | logo | logo | Name
Event program recognition | logo | logo | Name | Name
Website recognition | logo | logo | Name | Name
Gift Boxes | 20 | 10 | 5 | 5 | 1
Value of Boxes | 1000 | 500 | 250 | 250 | 50
| 20 gift boxes of $50 value/each delivered to you and guests - printed program | 10 gift boxes of $50 value/each delivered to you and guests - printed program | 5 gift boxes of $50 value/each delivered to you and guests - printed program | 5 gift boxes of $50 value/each delivered to you and guests - printed program | 1 gift boxes of $50 value/each delivered to you - printed program | Printed program - MAILED by OHU
Current sales
Total Boxes
Total cost of gift boxes | 0 | 0 | 0 | 0 |  | 0
Contributed Value
Value of Goods and Services Rec'd
Gift Boxes
Advertising/Media

## Lower Third Titles for Program
Name | Title
Dr. Charles A. Montorio-Archer | President and CEO, One Hope United
Kate Shaffer | Secretary of the Board of Directors & Fund Development Chair, One Hope United
Dreion | Keynote Speaker
David Young on behalf of The Young Family | 2021 Leadership in Giving Award Recipient
Jonni Miklos Finch | Presenter of the Ermit L. Finch Impact Award
Howard and Chris Schnitzer | 2021 Ermit L. Finch Impact Award Recipients
Flaviane Carvalho | 2021 President’s Award Recipient

## Run of Show
Time | Run Time | Program | Speaker(s) | Category | Who is producing it?
6:45 | 14:00 | Pre-Show |  | Pre-Produced | ESP
6:59 | 1:00 | Sponsor Loop |  | Pre-Produced | ESP
7:00 | 0:10 | Graphic Transition
7:00 | 3:00 | Intro Video |  | Pre-Produced | OHU
7:03 | 6:00 | Welcome and Remarks | Dr. Charles A. Montorio-Archer | Talking-Heads (Zoom) | ESP
7:09 | 0:03 | Graphic Transition
7:09 | 3:00 | Video: Mission Moment 1 | TBA | Pre-Produced | OHU
7:12 | 0:03 | Graphic Transition
7:12 | 2:00 | Appeal 1 | Kate Schaffer | Live | ESP
7:14 | 0:03 | Graphic Transition
7:14 | 10:00 | Keynote (may include a pre-recorded music video in this time) | Featured Guest – Dreion | Talking-Heads (Zoom) | ESP
7:24 | 0:03 | Graphic Transition
7:24 | 3:00 | Video: Mission Moment 2 | TBA | Pre-Produced | OHU
7:27 | 0:03 | Graphic Transition
7:27 | 2:00 | Appeal 2 | Kate Shaffer | Live | ESP
7:29 | 0:03 | Graphic Transition
7:30 | 10:00 | Conversation | Charles and Dreion | Talking-Heads (Zoom) | ESP
7:39 | 0:03 | Graphic Transition
7:40 | 2:00 | Leadership in Giving Award Presentation | Kate Shaffer | Talking-Heads (Zoom) | ESP
7:42 | 2:00 | Leadership in Giving Recipient | RJ Young on behalf of The Young Family | Talking-Heads (Zoom) | ESP
7:44 | 0:03 | Graphic Transition
7:44 | 2:00 | Ermit L. Finch Impact Award Presentation | Jonni Miklos | Talking-Heads (Zoom) | ESP
7:46 | 2:00 | Ermit L. Finch Impact Award Recipient | Howard and Chris Schnitzer | Talking-Heads (Zoom) | ESP
7:48 | 0:03 | Graphic Transition
7:48 | 2:00 | President's Award Presentation | Dr. Charles A. Montorio-Archer | Pre-Recorded Footage | OHU providing footage of the press conference event to be edited
7:50 | 2:00 | Preident's Award Recipient | Flaviane Carvalho | Pre-Recorded Footage | OHU providing footage of the press conference event to be edited
7:52 | 0:03 | Graphic Transition
7:52 | 3:00 | Video: Mission Moment 3 | TBA | Pre-Produced | OHU
7:55 | 0:03 | Graphic Transition
7:55 | 2:00 | Appeal 3 | Kate Schaffer | Live | ESP
7:57 | 0:03 | Graphic Transition
7:57 | 3:00 | Closing | Dr. Charles A. Montorio-Archer | Talking-Heads (Zoom) | ESP
8:00 | 2:00 | Closing Credits/Thank Yous |  | Pre-Produced | ESP

## Sponsors for Program
Keynote Sponsor - $10,000
Andrea Wirt
The Young Family
Patron Sponsor - $5,000
Carmela and Christopher Griffin
Illinois Toolworks
Host Sponsor - $1,500
Byron A. DeSilva
Christopher Hoffman
Daniel J. Horsley
Deanna Freise
Steve Sorenson
Scott Moeller